## Sheet1
Weeks
2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-18 | 2017-04-24 | 2017-05-02 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-11
Discusion for the project
Discusion for Type
Deviding tasks
Drawing Sketches
Req. Specification Document Draft
Writing Code
Discus Use Case & Sce.
Writing Use Cases
Writing Scenarios
Use Case Diagrams
Activity & State Diagrams
Sequence Diagrams
Writing Code
Collaboration Diagram
E-R Diagram
Database Scema
Class & Object Diagram
Component& Deployment Diagram
Software Code
Code Finish
Proj Management
Documentation Finish